## Professional
| Objectives: Get ____ new customers in 20__. Create awareness of __________. Engage, convert website visitors to customers. Increase customer wallet share to ______/average. |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | Estimated Cost | Actual Cost | Tracking Method | Expected Results | Leads | Cost per Lead | Actual Results | ROI
| Task | Resource | Due Date |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Analysis | Conduct Marketing Audit | New Incite | 2010-10-20 | √
Analysis | Provide Audit Findings/ Recommendations | Client | 2010-11-04 | √
Design | Design graphics - web/print/social media | New Incite | 2011-01-10 | [49 empty] | 2500 | 2200 | bar: January 1 to January 2
Design | Design revisions | New Incite | 2011-01-15 | bar: January 2
Design | Approve graphics | Client | 2011-01-20 | bar: January 3
PR | Press Releases | New Incite | Ongoing | [49 empty] | 1900 | 1850 | Web traffic | 25% Increase | 23 | 80.4348 | bar: January 2; January 4; February 2; February 4; March 2; March 4; April 2; April 4; May 2; May 4; June 2; June 4; July 2; July 4; August 2; August 4; September 2; September 4; October 2; October 4; November 2
PR | Draft press release | New Incite | Ongoing | [51 empty] | Online distr stats | bar: January 1; January 3; February 1; February 3; March 1; March 3; April 1; April 3; May 1; May 3; June 1; June 3; July 1; July 3; August 1; August 3; September 1; September 3; October 1; October 3; November 1; November 3
PR | Approve PR | Client | Ongoing | bar: January 1; January 3; February 1; February 3; March 1; March 3; April 1; April 3; May 1; May 3; June 1; June 3; July 1; July 3; August 1; August 3; September 1; September 3; October 1; October 3; November 1; November 3
Website | Get quote for site update | New Incite | 2011-01-05 | [49 empty] | 3000 | 2775 | Traffic, conversions | 70% Traffic; 20% Conv | 57 | 48.6842 | bar: January 1
Website | Update content | New Incite | 2011-01-10 | bar: January 2
Website | Program site/load content | New Incite | 2011-01-31 | bar: January 3 to January 4
Website | Install Google Analytics | New Incite | 2011-01-31 | bar: January 4
Website | Training on content management system | New Incite, Client | 2011-02-05 | bar: February 1
Website | Go Live | Client | 2011-02-10 | bar: February 2
Website | SEO - Optimize site for search engines | New Incite | Ongoing | [51 empty] | Search rankings | bar: February 3 to December 4
Email | Email campaigns: plan & schedule | New Incite | 2011-01-03 | [49 empty] | 7200 | 7200 | Opens, click thrus | Open 30%; Clicks 15% | 128 | 56.25 | bar: January 1
Email | Update database (new customers) | Client | Ongoing | bar: January 2; February 1; March 1; April 1; May 1; June 1; July 1; August 1; September 1; October 1
Email | Design email templates | New Incite | 2011-01-21 | bar: January 2 to January 3
Email | Write, get approval, distribute email | New Incite, Client | Ongoing
Social Media | Set up Social Media Platfomrs | New Incite | Ongoing | [51 empty] | # Likes | bar: May 1
Social Media | Post regular content | New Incite | Ongoing | bar: February 2 to December 4
TOTAL | [52 empty] | 14600 | 14025 |  |  | 208 | 67.4279